## Sheet1
Sep 15-21 | Sep 22-28 | Sep 29-Oct 05 | Oct 06-12 | Oct 13-19 | Oct 20-26 | Oct 27-Nov 02 | Nov 03-09 | Nov 10-16 | Nov 17-23 | Nov 24-30 | Dec 01-07 | Dec 08-14
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Define Project and Objectives | Define Project and Objectives
Start Graphic Chart/Logo... | Start Graphic Chart/Logo...
|  | README.md | Setup Github
Setup SERVER
|  |  |  | Start Front-end with tables | Improve .vue/clearer pages (more realistic)
Implement fully working CRUD JSON
Link DB to frontend
Create website front page
[8 empty] | Implement CRUD controllers |  | Implement login UI
[10 empty] | Link Login to DB |  | Bug Fixes
MAX | [11 empty] | Bug Fixes
ROLAND
BOTH