## Sheet1
Sep 15-21 | Sep 22-28 | Sep 29-Oct 05 | Oct 06-12 | Oct 13-19 | Oct 20-26 | Oct 27-Nov 02 | Nov 03-09 | Nov 10-16 | Nov 17-23
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Define Project and Objectives | Define Project and Objectives
Start Graphic Chart/Logo... | Start Graphic Chart/Logo...
|  | README.md | Setup Github
|  | Table structure diagram | Adding Diagrams (ER+Structure) | Use Case Diagram + Gantt
|  |  |  | .vue files + Use case Diagram | improve .vue/clearer pages
Link Datatbase to website
[7 empty] | Implements UI |  | Bug Fixes
[7 empty] | Implements New Fonctionalities(Log in...) |  | Bug Fixes
MAX
ROLAND